## Tabelle1
Time | Work | Milestones:
1-2 Weeks | Literature review | Selection of an active learning method, how can models be updated online?
3 Week | Case study implementation and data generation | Case study implemented for offline data generation and as a data stream
4 Week | Model generation (NARX or LSTM) | Selection of model, hyperparameters, training of the model
5 Week | Implementation into NMPC | Plant can be controlled via NMPC (using the ML model)
6-8 Week | Implementation and investigation of the active learning | Implementation of the selected AL method, able to detect data on which the model performs badly
end of 2 Month | First midterm | Feedback by Prof. Engell
3 Month | implementation of the online updating of the model | Model can be updated online
4 Month | Combining AL, NMPC und Online updating | Simulation study: ODE model is controlled via the NMPC (using the ML model) and updated when the AL method detects that the model performs badly
end of 4 Motnh | second midterm | Feedback by Prof. Engell
5 Investigation of the methods, etc. |  | Results are consistent
6. month | Writing | Written thesis :)